## Delivery Check List V 1.0
SNO | Area | Key Review Question | Inputs from Delivery | Reviewer Comments | RAG
1.1 | Scope, Planning & Governance | Are scope / SoW / baselines clearly defined, signed off, and tracked? | Yes
1.2 |  | Are change requests, assumptions, and dependencies captured and actively managed? | Yes
1.3 |  | Is the project plan (milestones, releases, critical path) realistic, updated, and communicated? | Yes
1.4 |  | Is governance cadence followed (status reviews, steering committee, reporting)? | Yes
1.5 |  | Are decision logs and action items tracked with owners and due dates? | Yes
2.1 | Delivery Health | Are milestones, sprints, and releases on track against plan (schedule variance within tolerance)? | Yes
2.2 |  | Are deliverables peer-reviewed and meeting acceptance / Definition of Done criteria? | Yes
2.3 |  | Are blockers, technical debt, and rework under control and visible in plans? | Yes
2.4 |  | Is release planning (scope, dates, dependencies) clear and agreed with stakeholders? | Yes
3.1 | Requirements & Customer Alignment | Are requirements / user stories clear, prioritized, approved, and version-controlled? | Yes
3.2 |  | Are acceptance criteria and non-functional requirements defined and agreed with the customer? | Yes
3.3 |  | Are backlog refinement, demos, and walk-throughs regularly done with key stakeholders? | Yes
3.4 |  | Are stakeholder communications timely, transparent, and documented? | Yes
3.5 |  | Are there any customer escalations, dissatisfaction signals, or relationship risks? | No
4.1 | Risks, Issues & Escalations | Are project risks, issues, assumptions, and dependencies logged, owned, and regularly updated? | Yes
4.2 |  | Are mitigations and contingency plans defined for high / critical risks? | Yes
4.3 |  | Are issues resolved within agreed SLA / timelines? | Yes
4.4 |  | Is the escalation matrix known, used effectively, and working as intended? | Yes
4.5 |  | Are repeated risks / issues feeding back into planning and process improvements? | Yes
5.1 | Resource & Team Management | Do we have the right mix of skills, capacity, and seniority to meet commitments? | Yes
5.2 |  | Are there any attrition, availability, or productivity gaps impacting delivery? | Yes
5.3 |  | Is there backup / succession for critical roles and single points of failure? | No
5.4 |  | Are onboarding, knowledge transfer, and role clarity adequate for new team members? | Yes
5.5 |  | How is team morale and collaboration (within the team and with the customer)? | Good
6.1 | Quality & Testing | Are unit, integration, and system tests executed with required coverage and documented results? | Yes
6.2 |  | Is UAT planned and executed with low defect leakage into production? | Yes
6.3 |  | Is test automation (functional / regression / smoke) leveraged appropriately? | NA
6.4 |  | Are code reviews, static analysis, and non-functional tests (performance, security, reliability) in place? | Yes
6.5 |  | Are defect trends monitored and corrective actions identified for recurring issues? | Yes
7.1 | Compliance & Security | Are organisational processes followed (SQA, documentation, approvals, audits)? | Yes
7.2 |  | Is customer data handled securely (access control, encryption, environments, masking)? | Yes
7.3 |  | Are any compliance risks (GDPR / PII / HIPAA / PCI / OSS licences) identified and managed? | Yes
7.4 |  | Are mandatory trainings, security guidelines, and policies adhered to by the team? | Yes
7.5 |  | Is evidence for audits (review records, logs, sign-offs) captured and stored properly? | Yes
8.1 | Financial Health | Is the project on budget (actuals vs planned, effort variance within agreed thresholds)? | Yes
8.2 |  | Is billing accurate, timely, and aligned with contract / SoW terms? | Yes
8.3 |  | Are margins and utilization aligned with targets and monitored regularly? | Yes
8.4 |  | Are scope / change decisions evaluated for commercial impact before commitment? | Yes
8.5 |  | Are there any forecasted financial risks (overruns, discounts, unapproved change orders)? | No
9.1 | Customer Success & Growth | What is the latest CSAT / NPS / qualitative feedback from the customer? | NA
9.2 |  | Is the customer getting measurable value and business outcomes from the engagement? | Yes
9.3 |  | Are we actively managing key stakeholders and influencing positively at multiple levels? | Yes
9.4 |  | Are there identified upsell, cross-sell, or expansion opportunities with clear next steps? | Yes
9.5 |  | Are we building references, success stories, or case studies with customer consent? | Yes
10.1 | Continuous Improvement & Knowledge Management | Are regular retrospectives / lessons-learned sessions conducted and actions tracked? | Yes
10.2 |  | Are best practices, templates, and checklists reused and improved across sprints / releases? | Yes
10.3 |  | Is project knowledge (designs, decisions, FAQs, runbooks) stored in a shared repository and kept current? | Yes
10.4 |  | Are metrics (quality, speed, stability, customer KPIs) used to drive continuous improvement? | NA
10.5 |  | Are transition, handover, and long-term maintainability aspects planned from early stages? | Yes