## Delivery Check List V 1.0
SNO | Area | Key Review Question | Inputs from Delivery | Reviewer Comments | RAG
1.1 | Scope, Planning & Governance | Are scope / SoW / baselines clearly defined, signed off, and tracked? | Yes
1.2 |  | Are change requests, assumptions, and dependencies captured and actively managed? | Yes
1.3 |  | Is the project plan (milestones, releases, critical path) realistic, updated, and communicated? | Yes
1.4 |  | Is governance cadence followed (status reviews, steering committee, reporting)? | Yes
1.5 |  | Are decision logs and action items tracked with owners and due dates? | Yes
2.1 | Delivery Health | Are milestones, sprints, and releases on track against plan (schedule variance within tolerance)? | Yes
2.2 |  | Are deliverables peer-reviewed and meeting acceptance / Definition of Done criteria? | Yes
2.3 |  | Are blockers, technical debt, and rework under control and visible in plans? | Yes
2.4 |  | Is release planning (scope, dates, dependencies) clear and agreed with stakeholders? | Yes
3.1 | Requirements & Customer Alignment | Are requirements / user stories clear, prioritized, approved, and version-controlled? | Yes
3.2 |  | Are acceptance criteria and non-functional requirements defined and agreed with the customer? | Yes
3.3 |  | Are backlog refinement, demos, and walk-throughs regularly done with key stakeholders? | Yes
3.4 |  | Are stakeholder communications timely, transparent, and documented? | Yes
3.5 |  | Are there any customer escalations, dissatisfaction signals, or relationship risks? | No
4.1 | Risks, Issues & Escalations | Are project risks, issues, assumptions, and dependencies logged, owned, and regularly updated? | Yes
4.2 |  | Are mitigations and contingency plans defined for high / critical risks? | Yes
4.3 |  | Are issues resolved within agreed SLA / timelines? | Yes
4.4 |  | Is the escalation matrix known, used effectively, and working as intended? | Yes
4.5 |  | Are repeated risks / issues feeding back into planning and process improvements? | Yes
5.1 | Resource & Team Management | Do we have the right mix of skills, capacity, and seniority to meet commitments? | Yes
5.2 |  | Are there any attrition, availability, or productivity gaps impacting delivery? | Yes
5.3 |  | Is there backup / succession for critical roles and single points of failure? | No
5.4 |  | Are onboarding, knowledge transfer, and role clarity adequate for new team members? | Yes
5.5 |  | How is team morale and collaboration (within the team and with the customer)? | Good
6.1 | Quality & Testing | Are unit, integration, and system tests executed with required coverage and documented results? | Yes
6.2 |  | Is UAT planned and executed with low defect leakage into production? | Yes
6.3 |  | Is test automation (functional / regression / smoke) leveraged appropriately? | NA
6.4 |  | Are code reviews, static analysis, and non-functional tests (performance, security, reliability) in place? | Yes
6.5 |  | Are defect trends monitored and corrective actions identified for recurring issues? | Yes
7.1 | Compliance & Security | Are organisational processes followed (SQA, documentation, approvals, audits)? | Yes
7.2 |  | Is customer data handled securely (access control, encryption, environments, masking)? | Yes
7.3 |  | Are any compliance risks (GDPR / PII / HIPAA / PCI / OSS licences) identified and managed? | Yes
7.4 |  | Are mandatory trainings, security guidelines, and policies adhered to by the team? | Yes
7.5 |  | Is evidence for audits (review records, logs, sign-offs) captured and stored properly? | Yes
8.1 | Financial Health | Is the project on budget (actuals vs planned, effort variance within agreed thresholds)? | Yes
8.2 |  | Is billing accurate, timely, and aligned with contract / SoW terms? | Yes
8.3 |  | Are margins and utilization aligned with targets and monitored regularly? | Yes
8.4 |  | Are scope / change decisions evaluated for commercial impact before commitment? | Yes
8.5 |  | Are there any forecasted financial risks (overruns, discounts, unapproved change orders)? | No
9.1 | Customer Success & Growth | What is the latest CSAT / NPS / qualitative feedback from the customer? | NA
9.2 |  | Is the customer getting measurable value and business outcomes from the engagement? | Yes
9.3 |  | Are we actively managing key stakeholders and influencing positively at multiple levels? | Yes
9.4 |  | Are there identified upsell, cross-sell, or expansion opportunities with clear next steps? | Yes
9.5 |  | Are we building references, success stories, or case studies with customer consent? | Yes
10.1 | Continuous Improvement & Knowledge Management | Are regular retrospectives / lessons-learned sessions conducted and actions tracked? | Yes
10.2 |  | Are best practices, templates, and checklists reused and improved across sprints / releases? | Yes
10.3 |  | Is project knowledge (designs, decisions, FAQs, runbooks) stored in a shared repository and kept current? | Yes
10.4 |  | Are metrics (quality, speed, stability, customer KPIs) used to drive continuous improvement? | NA
10.5 |  | Are transition, handover, and long-term maintainability aspects planned from early stages? | Yes

## Technical Check List V 1.0
# | Technical Area | Key Review Question | Inputs from Delivery | Reviewer Comments | RAG
1.1 | Architecture & Design | Who is responsible for the architecture and design ? (If Reflections, who is the named person ? If not Reflections, below questions on architecture will be more for mining and whitespace.) | Reflections - Sanju
1.2 |  | Is the target architecture documented and up to date (context, container, component, deployment diagrams)? How is the documentation stored, versioned, audited ? | Yes
1.3 |  | Are HLD and LLD available for all key modules and services? | Yes
1.4 |  | Are architectural decisions and trade-offs documented and aligned with business and technical requirements? | Yes
1.5 |  | Is the design modular, loosely coupled, scalable and maintainable? | Yes
1.6 |  | Are appropriate design patterns and reference architectures consistently applied? | Yes
1.7 |  | Is there a clear separation of concerns (UI, API, business logic, data, integration, cross-cutting services)? | Yes
1.8 |  | Is the integration approach (APIs, messaging, microservices, batch/ETL) clearly defined and consistent? | Yes
1.9 |  | Are cross-cutting concerns (configuration, logging, security, caching, observability) addressed in the design? | Yes
1.1 |  | Are non-functional requirements (performance, availability, reliability, security, compliance) captured and designed for? | Yes
1.11 |  | Are chosen technologies and platforms modern, supportable and aligned with enterprise standards and roadmap? | Yes
1.12 |  | Are deprecated or legacy components identified with a containment or migration plan? | NA
2.1 | Technical Documentation | Is system design and architecture documentation complete, accurate and version-controlled? | It is up to date. Older versions of architecture are overwritten
2.2 |  | Is API documentation (Swagger/OpenAPI, Postman collections, AsyncAPI, etc.) current and accessible to consumers? | NA
2.3 |  | Are installation, deployment and configuration steps clearly documented and validated on a clean environment? | Yes
2.4 |  | Is developer onboarding documentation available (local setup, coding standards, workflows)? | Yes
2.5 |  | Is user, admin and support documentation (SOPs, FAQs, runbooks) available where needed? | NA
2.6 |  | Are data models, ER diagrams and integration contracts documented and kept in sync with implementation? | Yes
2.7 |  | Are known issues, limitations and technical debt items documented with owners and target dates? | Maintained by Clients
3.1 | Data & Storage Design | Are data models and DB schemas appropriate for the workload and aligned to domain concepts? | Yes
3.2 |  | Are indexing, partitioning and sharding strategies adequate for expected scale and query patterns? | Yes
3.3 |  | Are critical queries reviewed and optimized using execution plans and performance metrics? | Yes
3.4 |  | Are backup and restore strategies defined, tested and documented for each data store? | Yes
3.5 |  | Are data retention, archival and purging policies defined and implemented in line with compliance needs? | Yes
3.6 |  | Is database security in place (RBAC, least privilege, encryption at rest, network controls, masking where needed)? | Maintained by Clients
3.7 |  | Is replication or high availability configured where required? | Yes
3.8 |  | Is data migration or integration strategy defined, including mapping, reconciliation and cutover plans? | NA
3.9 |  | Are data quality checks and constraints in place (not-null, referential integrity, validation rules)? | Yes
4.1 | Security Architecture | Is sensitive data (passwords, tokens, keys, PII, financial data) encrypted in transit and at rest? | Yes. As per clients data classification document, data that PDH recevies has no need for encryption
4.2 |  | Are authentication mechanisms aligned with enterprise standards (SSO, OAuth2/OIDC, MFA where required)? | NA
4.3 |  | Is authorization based on least privilege using well-defined roles and permissions (RBAC/ABAC)? | Client controlled
4.4 |  | Are secrets stored in an approved secrets vault and never hardcoded or committed to source control? | Clinet controlled. We use service accounts to execute the jobs.
4.5 |  | Are input validation, output encoding and security headers implemented to prevent common attacks? | Input validation is being done. Output encoding and sending files to downstream is handled by MFT team on clinet side
4.6 |  | Are checks in place for common vulnerabilities (XSS, SQL injection, CSRF, SSRF, insecure deserialization, etc.)? | NA, Maintainted by Clients
4.7 |  | Are third-party dependencies and container images regularly scanned and updated for vulnerabilities? | NA
4.8 |  | Is HTTPS/TLS enforced for all external and internal communications where appropriate? | NA
4.9 |  | Are security-relevant events logged without leaking sensitive data? | NA
4.1 |  | Are security reviews and tests (SAST, DAST, penetration tests where applicable) planned and tracked? | NA
5.1 | Code Quality & Standards | Is the codebase following agreed coding standards, naming conventions and folder structure? | Yes
5.2 |  | Are peer reviews or pull-request reviews performed for all non-trivial changes? | Yes
5.3 |  | Are hardcoded values, credentials and environment-specific parameters avoided and externalized to configuration or vaults? | Yes
5.4 |  | Is error handling consistent, with meaningful messages and no silent failures? | Yes
5.5 |  | Are reusable components and shared libraries used instead of copy-paste and duplication? | Yes
5.6 |  | Are unit tests present for core logic with meaningful assertions and acceptable coverage? | Yes
5.7 |  | Is version control used effectively (branching strategy, tagging, pull requests, release branches)? | Yes
5.8 |  | Are static analysis tools and linters enabled and free of critical issues before merging? | No
5.9 |  | Is dead code, unused configuration and feature flags regularly cleaned up? | Yes
5.1 |  | Is the code structured to support testability and extension (dependency injection, interfaces, clear boundaries)? | Yes
6.1 | Testing & Coverage | Is there a documented test strategy covering unit, integration, system, UAT, regression and smoke tests? | Yes
6.2 |  | Are test cases, test data and expected results documented and traceable to requirements or user stories? | Yes
6.3 |  | Are automated test suites integrated with CI/CD and run on every build or pull request for critical components? | No
6.4 |  | Is test coverage measured and are minimum thresholds defined for important modules? | Yes
6.5 |  | Are non-functional tests (performance, load, soak, security, failover) planned and executed where required? | Yes
6.6 |  | Are test environments representative of production in terms of configuration and integrations? | Yes
6.7 |  | Is defect tracking in place with clear ownership, priority and resolution SLAs? | Yes
7.1 | DevSecOps | Is a CI/CD pipeline implemented for build, test, security scans and deployment? | Yes
7.2 |  | Are environment configurations (Dev, QA, Pre-Prod, Prod) parameterized, separated and managed securely? | Yes
7.3 |  | Is a clear rollback or hotfix strategy defined and tested for failed deployments? | Yes
7.4 |  | Is infrastructure-as-code (Terraform, ARM/Bicep, CloudFormation, Ansible, Helm, etc.) used where applicable? | Mainatined by clinets
7.5 |  | Are deployment scripts, IaC templates and pipeline definitions version-controlled and peer-reviewed? | Yes
7.6 |  | Are SAST, DAST, software composition analysis and container image scans integrated into pipelines with gating policies? | NA
7.7 |  | Are secrets and credentials in pipelines managed through a secure secrets store and never embedded in code? | Yes
7.8 |  | Are backups, restore procedures and DR runbooks validated through regular drills or simulations? | Maintained by Clients
7.9 |  | Are CI/CD tools themselves secured with access control, audit trails and least-privilege permissions? | Maintained by Clients
8.1 | Environments & Infrastructure | Is Dev/QA/UAT/Pre-Prod/Prod parity maintained for key components and configurations? | Yes
8.2 |  | Are environments provisioned and updated via IaC and configuration management tools? | Maintained by Clients
8.3 |  | Are capacities right-sized with headroom for growth and peak loads, and is auto-scaling used where relevant? | Maintained by Clients
8.4 |  | Are recent build or environment failures analyzed with RCA and corrective actions tracked? | Maintained by Clients
8.5 |  | Are high-availability and resilience mechanisms in place (clusters, load balancers, multi-AZ or multi-node)? | Maintained by Clients
8.6 |  | Are network configurations (VPC/VNet, firewalls, security groups, ingress/egress rules, VPN) reviewed and documented? | Maintained by Clients
8.7 |  | Are environment-specific settings externalized and managed securely (no secrets in flat files checked into Git)? | Yes
9.1 | Operational Readiness & Reliability | Is centralized, structured logging in place with correlation IDs to trace requests across services? | NA
9.2 |  | Are metrics and dashboards defined for key SLIs such as latency, error rate, throughput and resource usage? | NA
9.3 |  | Are alerts configured with meaningful thresholds, noise reduction and linked runbooks? | NA
9.4 |  | Is there a clear on-call model and escalation matrix for production incidents? | Yes
9.5 |  | Are support processes, SOPs, runbooks and troubleshooting guides documented and maintained? | Yes
9.6 |  | Has the system passed an agreed go-live or operational readiness checklist? | Yes
9.7 |  | Are incident management and RCA processes defined with follow-up actions for recurring issues? | Yes
10.1 | Compliance & Governance | Are licensing requirements for all third-party tools, libraries and platforms understood and compliant? | Maintained by Clients
10.2 |  | Is the solution compliant with applicable data protection and privacy regulations and internal policies? | Yes
10.3 |  | Are audit logs enabled for critical business and security events and stored securely with defined retention? | Maintained by Clients
10.4 |  | Are data classification and handling rules applied to PII and other sensitive data with appropriate controls? | Yes
10.5 |  | Are data retention, archival and deletion policies defined, implemented and aligned with legal requirements? | Yes
10.6 |  | Are access reviews, segregation of duties and approval workflows in place for privileged operations and changes? | Maintained by Clients
11.1 | Performance, Scalability & Resilience | Are target NFRs for latency, throughput, concurrency and availability defined and agreed? | Yes
11.2 |  | Have load, stress and endurance tests been executed using realistic workloads and data volumes? | Yes
11.3 |  | Are performance bottlenecks identified, profiled and tracked with action items? | Yes
11.4 |  | Are caching, batching and asynchronous processing used where appropriate to improve performance? | NA
11.5 |  | Are resiliency patterns such as timeouts, retries, circuit breakers and bulkheads implemented and tested? | NA
11.6 |  | Is capacity planning done for peak load, growth and burst scenarios with monitoring to validate assumptions? | Yes
12.1 | APIs, Integrations & Messaging | Are all inbound and outbound integrations clearly listed with owners, SLAs and failure modes? | Yes
12.2 |  | Are API and message contracts documented and versioned (OpenAPI, AsyncAPI, schema registry, etc.)? | NA
12.3 |  | Are API gateways or integration platforms configured for authentication, routing, throttling and logging? | NA
12.4 |  | Are error handling, timeouts, retries and idempotency behaviour defined and implemented for all integrations? | Yes
12.5 |  | Are contract tests or automated integration tests in place for critical APIs, queues and topics? | NA
12.6 |  | Are message schemas, routing keys, queues and topics documented and governed to avoid breaking changes? | NA
13.1 | User Experience & Accessibility | Are key user journeys and personas identified and tested end-to-end? | NA
13.2 |  | Is the UI consistent with the design system or style guide for layout, typography and interactions? | NA
13.3 |  | Is the application responsive and usable across supported devices, browsers and screen sizes? | NA
13.4 |  | Are accessibility guidelines (for example WCAG 2.1) considered and tested where required? | NA
13.5 |  | Is internationalization and localization supported where needed (text resources, date/time, currency, RTL)? | NA
13.6 |  | Are error states and long-running operations communicated clearly to users? | NA
14 | AI Adoption | • How are you currently using AI across different stages of development (coding, testing, design, documentation, DevOps)? • What steps do you take to verify the correctness, security, and quality of AI-generated code or artifacts? • Do you use AI to support architectural decisions, requirement clarification, or solution design? If yes, how? • How has AI impacted your productivity, speed, or ease of development in your day-to-day work? • Are you aware of and following any guidelines or restrictions for using AI tools (e.g., data sharing, code ownership, compliance)? | Using Copilot/chatgpt while coding Testing the code generaed by AI AI is not currently used for architectural decisions Dev work has seen increased speed improving productivity NO